## Earthworks (hidden)
INFORMATIVE | [6 empty] | COMPUTATIONAL | [5 empty] | GRAPHIC
Building | Phase/ Operation | no. | Name | Specific Units | No. of SU | Standard hours per specific unit | Standard hours in sum | Shift working | Operating (working) voltage | No. of workers |  | Total time | Number of Working Days
|  |  |  | [SU] |  | [Sh/SU] |  |  | [%] | In - house | Foreign |  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4
[13 empty] | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
SO.01 | Earthworks | 1 | Site Inspection and Preparation | set | x | 2 | 2 | 1 | x | 3 | 0 | 2 | bar: 1 1
|  | 2 | Construction Site Levelling (roughly) | set |  | 3 |  |  | x | bar: 1 1
|  | 3 | Erection of a Fence | m2 |  | 0.061 |  |  | 100 | bar: 1 1
|  | 4 | Tree Removal | piece |  | viz. table | bar: 1 2 to 1 3
|  | 5 | Removal of Shrubs | m2 |  | 0.17 | bar: 1 3
|  | 6 | Burning of Gathered Vegetation | set |  | 5
|  | 7 | Topsoil Removal | m3 |  | 0,014 - 0,02*
|  | 8 | Levelling of the Building | set |  | 3 - 5
|  | 9 | Bench Marks Assembly | piece |  | 0.48
|  | 10 | Levelling of the Foundation Pit | 100 m |  | 7.67
|  | 11 | Excavation of Foundation Pit | m3 |  | 0.0386
|  | 12 | Levelling of theFoundation Trenches | 100 m |  | 7.67
|  | 13 | Excavation of Foundation Trenches | m3 |  | 0.0386
|  | 14 | Manual Final Treatment | m3 |  | 1,94 - 2,7

## ŠABLONA
DATA PRO HARMONOGRAM, CYKLOGRAM A SÍŤOVÝ GRAF
n = | doplňte Vaše číslo n
Číslo | Název činnosti | Množství | Počet prac. | Produktivita | 1.NP (100%) | Provádění | 2.NP (80%) | Provádění | 3.NP (55%) | Provádění | 4.NP (40%) | Provádění
|  | tis. Kč |  | KČ/Nh/prec. | tis. Kč | dny | tis. Kč | dny | tis. Kč | dny | tis. Kč | dny
1 | zdi nosné | 850+20n | 8 | 1272
2 | stropy | 830+20n | 10 | 1140
3 | podlahy z dlaždic | 174+3n | 5 | 773
4 | výplně otvorů | 150+3n | 2 | 7360
5 | příčky | 56+2n | 4 | 833
6 | kanalizace vnitřní | 50+2n | 2 | 771
7 | zařizovací předměty | 114+2n | 3 | 3119
8 | omítky | 348+5n | 10 | 438
9 | silnoproud kompletace | 130+3n | 2 | 3966
10 | mtž otopných těles | 88+2n | 2 | 2232
11 | osazení zárubní - obložkových | 58+2n | 2 | 1325
12 | podhledy ze SDK | 73+2n | 2 | 1450
13 | podlahové konstrukce | 144+3n | 6 | 762
14 | obklady vnitřní | 140+3n | 5 | 615
15 | silnoproud vodiče | 60+2n | 2 | 947
16 | malby vnitřní | 46+2n | 4 | 342
17 | osazení zárubní - ocelových | 38+2n | 2 | 955
18 | rozvody ÚT | 164+3n | 6 | 923
19 | vodovod vnitřní | 64+2n | 4 | 635

## HARMONOGRAM
HARMONOGRAM PRO JEDNO PODLAŽÍ
n = | doplňte Vaše číslo n
Informativní část | [7 empty] | Výpočtová část | [5 empty] | Grafická část
Stavební objekt | Podlaží | Č. | Název činnosti | Množství | Počet M.J. | Nh / M.J. (produktivita) | Pracnost skutečná [Ph] | Směnnost | Počet hodin ve směně | Napětí | Počet pracovníků |  | Celková doba | Počet pracovních týdnů / dnů
|  |  |  | [tis kč] |  | [Kč/Nh/prac.] |  |  |  | [%] | vlastní | cizí |  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4
[14 empty] | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
SO.01 | 1NP | 1 | zdi nosné |  | 850+20n | 1272 |  | 1 | 8 | 100 | 8 | 0 | bar: 1 1 to 3 1
|  | 2 | stropy |  | 830+20n | 1140 |  | 1 | 8 | 100 | 10 | 0 | bar: 1 5 to 3 4
|  | 3 | podlahy z dlaždic |  | 174+3n | 773 |  | 1 | 8 | 100 | 5 | 0
|  | 4 | výplně otvorů |  | 150+3n | 7360 |  | 1 | 8 | 100 | 2 | 0
|  | 5 | příčky |  | 56+2n | 833 |  | 1 | 8 | 100 | 4 | 0
|  | 6 | kanalizace vnitřní |  | 50+2n | 771 |  | 1 | 8 | 100 | 2 | 0
|  | 7 | zařizovací předměty |  | 114+2n | 3119 |  | 1 | 8 | 100 | 3 | 0
|  | 8 | omítky |  | 348+5n | 438 |  | 1 | 8 | 100 | 10 | 0
|  | 9 | silnoproud kompletace |  | 130+3n | 3966 |  | 1 | 8 | 100 | 2 | 0
|  | 10 | mtž otopných těles |  | 88+2n | 2232 |  | 1 | 8 | 100 | 2 | 0
|  | 11 | osazení zárubní - obložkových |  | 58+2n | 1325 |  | 1 | 8 | 100 | 2 | 0
|  | 12 | podhledy ze SDK |  | 73+2n | 1450 |  | 1 | 8 | 100 | 2 | 0
|  | 13 | podlahové konstrukce |  | 144+3n | 762 |  | 1 | 8 | 100 | 6 | 0
|  | 14 | obklady vnitřní |  | 140+3n | 615 |  | 1 | 8 | 100 | 5 | 0
|  | 15 | silnoproud vodiče |  | 60+2n | 947 |  | 1 | 8 | 100 | 2 | 0
|  | 16 | malby vnitřní |  | 46+2n | 342 |  | 1 | 8 | 100 | 4 | 0
|  | 17 | osazení zárubní - ocelových |  | 38+2n | 955 |  | 1 | 8 | 100 | 2 | 0
|  | 18 | rozvody ÚT |  | 164+3n | 923 |  | 1 | 8 | 100 | 6 | 0
|  | 19 | vodovod vnitřní |  | 64+2n | 635 |  | 1 | 8 | 100 | 4 | 0